## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Tasks to Be Completed
| Table 1 | Tasks to Be Completed
Team Readiness - Stoplights
| Table 1 | Team Readiness - Stoplights
Social & PR Promo Plan
| Table 1 | Social & PR Promo Plan

## Tasks to Be Completed
Product Version or Name | Task/Deliverable/Asset | DRI/Owner | Copy finalized by (date): | Localization Status (details on which languages have been completed, if applicable) | Requires Legal Review? | With Legal Team for Review? | Signed off by Legal Team? | Date to set live | Live? | Team | Notes
Alpha - Example Row | Press release | Jen | 2019-01-01 | ES completed | NO | N/A | N/A | 2019-02-01 | N/A | Product Marketing
Alpha - Example Row | Customer alert email | Michel | 2019-01-01 | ES completed | YES | YES | IN PROGRESS | 2019-01-20 | NOT YET | Customer Marketing
Alpha - Example Row | Home page promotional video | Jeremiah | 2019-01-01 | N/A | YES | NOT YET | N/A | 2019-02-01 | NOT YET | Product Marketing
Alpha - Example Row | In-app product update | Holly | 2019-01-01 | ES completed | YES | YES | YES | 2019-02-02 | YES | Engineering
Alpha - Example Row | Product spotlight video | Alexandre | 2019-01-01 | N/A | YES | NOT YET | N/A | 2019-02-03 | NOT YET | Video Team

## Team Readiness - Stoplights
Last updated | Department | Team | Directly Responsible Individual | Details on Assets You're Creating | Overall Readiness | Roadblocks / Concerns | Asset Links
2019-01-01 | Marketing | Website Team | Jorge | Alter pricing page to reflect new packaging options Copywriting for home page Front-end design for redesigned pricing page | On track - in progress | None
2019-01-01 | Marketing | Social Media | Jamie | All social promotion across all platforms Copywriting for paid promotion Creative assets for social posts | Ready to go | None
2019-01-01 | Product | Mobile | Alexandre | All mobile versions of Alpha V2 features | On track - not yet begun | None
2019-01-01 | Legal | Legal | Samantha | Approval of updated: - Pricing page copy - Terms of Service - Privacy Policy | Slight concern - have not started | Awaiting pricing page copy from Website Team

## Social & PR Promo Plan
Publish Date | Publish Time | Platform | Directly responsible individual | Copy ready? | Creative ready, if applicable? | Link to draft within social tool | Publish Status
2019-02-01 | 33:00 | LinkedIn | Jamie | YES | YES |  | Not yet live
2019-02-01 | 33:00 | Instagram | Jamie | YES | YES |  | Not yet live